## UI
UI development
TaskID | Date Assigned | Category | Developer | Delivered-1 | Delivered-2 | Delivered-3 | Short Description | Comments if any
1001 | 2021-04-01 | NZ-Archive Purge records | Nishidh | 2021-04-12 |  |  | 1) Implement functionality for purgeNow.2) Display Parameters next to log categories.3) Implement functionality for Reset Archieve Data | As per discussion Purge Report functionality is on hold
1002 | 2021-04-21 | SM-SAAS Project Configuration UI changes | Nishidh | 2021-04-28 |  |  | Display DataSource,TemplateFilePath,BackupFilePath,MDFFilePath,LDFFilePath from web.config and implement CRUD operation for Saas Parameter.
1003 |  | SQL Task
1004 | 2021-04-30 | SAAS customer DB Download | Nishidh | 2021-05-10 |  |  | 1)List Customer Databases 2) Download functionality of Backup 3) Upload functionality 4) Application parameter settings for downlaod and upload size | As per discussion tested file limit for download/upload - 1GB
1005 | 2021-05-13 | Add Other Settings and Sort discovery methods | Nishidh | 2021-05-15 |  |  | 1) add other settings to 3rd party intigrations 2) disable buttons 3) add sorting functionality for discovery methods 4) save sorting order of discovery methods
1006 | 2021-05-19 | Saas Server Configuration | Nishidh | 2021-05-20 | 2021-05-25 | 2021-05-28 | 1) Created API to check Server is configured or not 2) made UI changes to call the API 3) changed UI to call Prashant's API 4) Worked on feedback points given by gopichand 5) Created Container form with name Saas_Server_Container 6) Changed UI using newly created form
1007 | 2021-05-26 | Property Grid tooltip styling | Nishidh | 2021-05-28 |  |  | 1) changed default tooltip with custom tooltip 2) checked all form location where property grid is used 3) updated new CSS in style.override.css file for common use
1008 | 2021-06-02 | Grid Extender-control enhancement | Nishidh | 2021-06-08 | 2021-06-16 | 2021-06-22 | 1) Hide Column,Sort column,Move column,tooltip on column 2) Get and Set Column width and order 3) Export and Delete and Edit function 4) Working on dynamic pagination as discussed 5) Add default CheckBox control beside Delete Button in current grid extender. 6) Add a Property textbox which will take the number of columns which are not editable. 7) Add Filter option like selecting number of fields for search in. 8) Given functionality for export all records to PDF/Excel 9) Export checked records only | Reoderable,Tooltip,Export,Delete and Edit columnMenu properties and Events like reorderColumn,resizeColumn,remove,save and dataBinding
1009
1010 | 2021-06-17 | Listview Extender | Nishidh | 2021-06-21 |  |  | 1) Added New List Extender from database with properties and events 2) Search functionality 3) Sorting functionality 4) Buttons like add,delete clone added
1011 | 2021-06-22 | SQL Solution and Services-UI devlopment | Nishidh | 2021-06-28 | 2021-07-01 |  | 1) Add new control sidemenu with default facility 2) API called for get all solution and services 3) UI changes as described in the document 4) Worked on feedback points like add click event for settings and help button,one solution should open at a time, click event for item selection, remove up-down icon. 5) Add reorder button 6) open popup with defied functionality like sort services,hide icons,save to DB functionality.
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024

## SQL
SQL development
TaskID | Date Assigned | Category | Developer | Delivered-1 | Delivered-2 | Delivered-3 | Short Description | Comments if any
1001 | 2021-04-01 | NZ-Archive Database | Prashant | 2021-04-12 |  |  | Created Required StoredProcedures to Purged data of Notification Tables from Master database to Archive Database. It will create the DB on fly( if not exists ) and takes the backup at the end of purging the data and delete the same from Master database | As per discussion Purge Report functionality is on hold
1002 | 2021-04-21 | CRUD Operation SPs of NZInfo Table in NzSaas DB | Prashant | 2021-04-22 |  |  | Created the Create, Update, Delete records Sps and Get record(s) Sp of NZInfo Table in NzSaas Database
1003 | 2021-04-27 | Saas Project JOB | Prashant | 2021-04-29 |  |  | Created Table to store SaasCustomerledger, Created Sp to get and insert customer rack,user and site count from their respective database into the Saas DB table. Schedule a Job to perform the action daily at 2:00:00 PM
1004 | 2021-04-30 | SAAS customer DB Download | Prashant | 2021-05-10 |  |  | Created required Stored Procedures , Functions, Type in NzEnt and NzSaas Database for the Upload and Download DataBase functionality. CONFIG_spCreateBackUpAndGetData CONFIG_spSaveBakFile
1005
1006 | 2021-05-13 | Saas Server Configuration | Prashant | 2021-05-20 | 2021-05-25 |  | 1) Created API for Restoring NzSaas Database (4 methods - 1 in SaasService.svc.cs and 3 in NzServermangerment..cs) 2) Added new DataSource column to SAAS.instances table and updated Stored Procedure(SAAS_spSetServerInstanceForSaas) to Add/Update DataSource column value
1007 |  | UI-task
1008 | 2021-06-02 | Grid Extender-control enhancement | Prashant | 2021-06-08 |  |  | Added 7 Column in NZ.ValueByName Table and updated the 2 Sps to insert and update the column Values
1009 | 14/06/2021 | Purge and Optimize SM Application | Prashant | 16/06/2021 | 18/06/2021 |  | 1) Document is provided which has both SQL and WebService changes. Divided into phases. 2) Phase 1 :- SQL side changes, Create Tracemethod and supported StoredProcedure to update the existing all SP and store the record in Tracemethod if they are used in the 3) Create the Delete record (SPs,Function and Table) SPS which are not in Tracemethod table. | As per the discussion we listed out the 48 Sps which are not able to alter the SP. So, as per the discussion with Yadav - their team will go through and take necessary action on those SPs and gave us new Databse where we can execute the SP and update the scripts with required changes after testing. Will then provide to yadav to test whole application and then we can take the further phase with Webservice and purging the data from the database and application
1010
1011 | 2021-06-22 | SQL Solution and Services-UI devlopment | Prashant |  |  |  | 1) Document is provided and need to create 4 tables + 1 testing table and respective Sps as mentioned in the document and done testing with provided testing data as well as manually added data 2) Work on the feedback points and new addition to the SPs
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024