## UI
UI development
TaskID | Date Assigned | Category | Developer | Delivered-1 | Delivered-2 | Delivered-3 | Short Description | Comments if any
1001 | 2021-04-01 | NZ-Archive Purge records | Nishidh | 2021-04-12 |  |  | 1) Implement functionality for purgeNow.2) Display Parameters next to log categories.3) Implement functionality for Reset Archieve Data | As per discussion Purge Report functionality is on hold
1002 | 2021-04-21 | SM-SAAS Project Configuration UI changes | Nishidh | 2021-04-28 |  |  | Display DataSource,TemplateFilePath,BackupFilePath,MDFFilePath,LDFFilePath from web.config and implement CRUD operation for Saas Parameter.
1003 |  | SQL Task
1004 | 2021-04-30 | SAAS customer DB Download | Nishidh | 2021-05-10 |  |  | 1)List Customer Databases 2) Download functionality of Backup 3) Upload functionality 4) Application parameter settings for downlaod and upload size | As per discussion tested file limit for download/upload - 1GB
1005 | 2021-05-13 | Add Other Settings and Sort discovery methods | Nishidh | 2021-05-15 |  |  | 1) add other settings to 3rd party intigrations 2) disable buttons 3) add sorting functionality for discovery methods 4) save sorting order of discovery methods
1006 | 2021-05-19 | Saas Server Configuration | Nishidh | 2021-05-20 | 2021-05-25 | 2021-05-28 | 1) Created API to check Server is configured or not 2) made UI changes to call the API 3) changed UI to call Prashant's API 4) Worked on feedback points given by gopichand 5) Created Container form with name Saas_Server_Container 6) Changed UI using newly created form
1007 | 2021-05-26 | Property Grid tooltip styling | Nishidh | 2021-05-28 |  |  | 1) changed default tooltip with custom tooltip 2) checked all form location where property grid is used 3) updated new CSS in style.override.css file for common use
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024

## SQL
SQL development
TaskID | Date Assigned | Category | Developer | Delivered-1 | Delivered-2 | Delivered-3 | Short Description | Comments if any
1001 | 2021-04-01 | NZ-Archive Database | Prashant | 2021-04-12 |  |  | Created Required StoredProcedures to Purged data of Notification Tables from Master database to Archive Database. It will create the DB on fly( if not exists ) and takes the backup at the end of purging the data and delete the same from Master database | As per discussion Purge Report functionality is on hold
1002 | 2021-04-21 | CRUD Operation SPs of NZInfo Table in NzSaas DB | Prashant | 2021-04-22 |  |  | Created the Create, Update, Delete records Sps and Get record(s) Sp of NZInfo Table in NzSaas Database
1003 | 2021-04-27 | Saas Project JOB | Prashant | 2021-04-29 |  |  | Created Table to store SaasCustomerledger, Created Sp to get and insert customer rack,user and site count from their respective database into the Saas DB table. Schedule a Job to perform the action daily at 2:00:00 PM
1004 | 2021-04-30 | SAAS customer DB Download | Prashant | 2021-05-10 |  |  | Created required Stored Procedures , Functions, Type in NzEnt and NzSaas Database for the Upload and Download DataBase functionality. CONFIG_spCreateBackUpAndGetData CONFIG_spSaveBakFile
1005
1006 | 2021-05-13 | Saas Server Configuration | Prashant | 2021-05-20 | 2021-05-25 |  | 1) Created API for Restoring NzSaas Database (4 methods - 1 in SaasService.svc.cs and 3 in NzServermangerment..cs) 2) Added new DataSource column to SAAS.instances table and updated Stored Procedure(SAAS_spSetServerInstanceForSaas) to Add/Update DataSource column value
1007 |  | UI-task
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024